## Project RA
Potential risk | Severity | Likelihood | Risk Mitigation
Members take on other commitments conflicting with meetings | Low-Medium | Medium | Fill out a when-to-meet to find new meeting time
Members do not complete tasks on time | Medium | Medium | Distribute work better among teammates or fix time management for the individual. Our schedule gives us 2 free weeks to work with in case this process becomes extensively long.
Member becomes sick | High | Low | Take parts of system that are complete and try to work around them
Member misses single meeting or part of meeting | Low | High | Tell member what he missed and his responsibilities
Final system crashes | Medium | Medium-High | Use binary search with print statements to find the part of code that crashes, and then have the member in charge of that module communicate with the members of the surrounding modules to identify the problem
Individual modules fail when testing communication with surrounding modules | Low | High | Have members that are in charge of those modules meet and debug the problem

## CTC Office
Ritesh's Risk Table
Potential Risk | Severity | Likelihood | Action Plan
RAS meeting times changed to conflict with 1186 group meeting time | Low | Medium | Miss RAS or ask group members to change time
Failing to complete module on time | Low to high depending on what point we are in the semester | Medium | Appropriate time from other activities to catch up and maybe redistribute tasks if the group deems it necessary
CTC office not sending/setting authority properly | Medium | High | Look through code I have written and then talk to Jeff(wayside controller) about the error if I cannot find anything wrong with my code
CTC office not loading schedule properly based on information from wayside controller | Medium | High | Use print statements to examine data being received from wayside controller. If the data looks right based on all of the inputs, examine my own code to make sure I am interpreting and displaying it properly
CTC office missing a specification or carrying out a function properly but not in the way it is supposed to | Medium | High | If I doubt anything that I am doing, first ask team members/look through notes, and if I am still confused ask in class/Courseweb
CTC office UI slowly becomes difficult to use | Medium | Medium | Constantly ask group for feedback on UI, adjust the UI as I add functionality so that it continues to be easy to use
The .jar file of my project fails to load on my group member's machine when we are testing for presentation | Low | Medium | Move source code over to group member's computer and have them generate a jar file the way they usually do it so that the jar file works on their computer and so that the entire system works.
My computer fails to project on the projector when I am presenting my module | High | Medium | Test all of our computers with the projector beforehand, and make sure all of the files we need to present are loaded on every computer beforehand.
CTC office units not compatible with units that wayside controller expects | Low | High | Talk to Jeff (wayside controller) and agree on common units to use. Best to check that these units are maintained throughout the flow of the program, with the exception of displaying things to users who only know miles/feet

## Track Contoller
Jeff Deely's Risk Table
Potential Risk | Severity | Likelihood | Action Plan
Failure to Complete Task on time | low to severe depending on which task and how late it is in the semester | Medium | Make sure that tasks are completed two weeks before any due date
Computer Breakdown/ Loss of all files in memory | severe | low | Back up all code files on a second hardrive, Back up all files on github
Power Outage when working | High | Medium | Save files often when working on them
Personal Emergancy | High | low | If possible continue to work on project, if not module will have to go to another person in the group
Communiccation failure between Track Controller and other Modules | Medium | High | Meet regularly and make sure that everyone knows what needs to be sent and in what form it should be sent
Accidentally Overwrite File on Github with previous iteration | Medium | Medium | Keep local, well maintained files updated with most recent work
PLC code cannot be found | High | low | Make sure that all PLC code is save in the modules folder
Projector Failure | Low | Medium | Come into class an hour earlier to make sure that everything displays properly

## Track Model
Spencer Worms's Risk Table
Potential Risk | Severity | Likelihood | Action Plan
Failing to complete module on time | High | Medium | Schedule more time to work on module than expected
Computer crash, losing files | High | Low | Back up all code to GitHub to ensure that the files still exist
Computer loses power while working | Medium | Low | Save files often to both my computer and the team GitHub
Withdraw from class | High | Low | Work already done on the module will be given to the group and they will have to work on it
Personal emergency | Medium | Low | Work with group to determine if I can work on my module still, or get someone else to help work on it
Communication failure with the other modules | Low | Medium | Work closely with the other team members to ensure good communication and complete work eariler to account of time to fix the issue
Have issues projecting my modules when presenting | Medium | Medium | Test the computer before hand and have backup on a flash drive to give to someone else to present on their computer