## Project RA
Potential risk | Severity | Likelihood | Risk Mitigation
Members take on other commitments conflicting with meetings | Low-Medium | Medium | Fill out a when-to-meet to find new meeting time
Members do not complete tasks on time | Medium | Medium | Distribute work better among teammates or fix time management for the individual. Our schedule gives us 2 free weeks to work with in case this process becomes extensively long.
Member becomes sick | High | Low | Take parts of system that are complete and try to work around them
Member misses single meeting or part of meeting | Low | High | Tell member what he missed and his responsibilities
Final system crashes | Medium | Medium-High | Use binary search with print statements to find the part of code that crashes, and then have the member in charge of that module communicate with the members of the surrounding modules to identify the problem
Individual modules fail when testing communication with surrounding modules | Low | High | Have members that are in charge of those modules meet and debug the problem

## CTC Office
Ritesh's Risk Table
Potential Risk | Severity | Likelihood | Action Plan
RAS meeting times changed to conflict with 1186 group meeting time | Low | Medium | Miss RAS or ask group members to change time
Failing to complete module on time | Low to high depending on what point we are in the semester | Medium | Appropriate time from other activities to catch up and maybe redistribute tasks if the group deems it necessary
CTC office not sending/setting authority properly | Medium | High | Look through code I have written and then talk to Jeff(wayside controller) about the error if I cannot find anything wrong with my code
CTC office not loading schedule properly based on information from wayside controller | Medium | High | Use print statements to examine data being received from wayside controller. If the data looks right based on all of the inputs, examine my own code to make sure I am interpreting and displaying it properly
CTC office missing a specification or carrying out a function properly but not in the way it is supposed to | Medium | High | If I doubt anything that I am doing, first ask team members/look through notes, and if I am still confused ask in class/Courseweb
CTC office UI slowly becomes difficult to use | Medium | Medium | Constantly ask group for feedback on UI, adjust the UI as I add functionality so that it continues to be easy to use
The .jar file of my project fails to load on my group member's machine when we are testing for presentation | Low | Medium | Move source code over to group member's computer and have them generate a jar file the way they usually do it so that the jar file works on their computer and so that the entire system works.
My computer fails to project on the projector when I am presenting my module | High | Medium | Test all of our computers with the projector beforehand, and make sure all of the files we need to present are loaded on every computer beforehand.
CTC office units not compatible with units that wayside controller expects | Low | High | Talk to Jeff (wayside controller) and agree on common units to use. Best to check that these units are maintained throughout the flow of the program, with the exception of displaying things to users who only know miles/feet

## Track Contoller
T